ATTACHMENT A

Statement of Work

IPAWS Implementation Support Services

December 10, 2008

1.	GENERAL	3

1.1	Background	3

1.2	Scope	3

1.2.1 Inventory, Database and System Evaluation	3

1.2.2 EAS Modernization and Expansion	3

1.2.3 National and State Digital EAS	3

1.2.4 IPAWS Emergency Truck Implementation	3

1.2.5 Additional IPAWS Implementation Services	3

2.	REFERENCES	3

2.1	General Standards	3

2.2	FEMA Specific Standards	3

2.3	Technical Standards	3

2.4	Security Standards	3

2.5	Training and Exercises Standards	3

3.	TASKS AND REQUIREMENTS	3

3.1	Project Management	3

3.1.1	Program Planning	3

3.1.2	Performance Metrics	3

3.1.3	Earned Value Management	3

3.1.4	Risk Response Management	3

3.2 Inventory and Evaluation	3

3.3  Implementation Engineering	3

3.4 Facility Design and Construction	3

3.4.1 Comprehensive Implementation Plans (CIP)	3

3.4.2 Site Notifications	3

3.4.3 Work Requirements	3

3.5 Testing and Acceptance	3

3.6 System Configuration	3

3.7 Operations and Maintenance Support.	3

4	PERSONNEL SECURITY	3

5	NONDISCLOSURE OF SENSITIVE AND/OR PROPRIETARY DATA	3

# GENERAL

This Statement of Work (SOW) defines the tasks to provide implementation services to the Integrated Public Alert and Warning System (IPAWS) Program.  The IPAWS Implementation Support Services (ISS) contract will provide engineering design services, perform alert and warning system inventory, database and evaluation, accomplish system development, acquire hardware and software, perform facility modification and construction, installation, integration testing and operational support services to federal, state and local communities in deploying IPAWS. The ISS contract is an Indefinite Delivery, Indefinite Quantity (IDIQ) contract type. Actual work will be authorized by issuance of Task Orders.

## 1.1	Background

As the nation’s primary emergency response agency, FEMA serves as the Federal Executive Branch’s (FEB) Lead Agent for Continuity of Operations (COOP) and Contingency Programs. A critical component of this function is the establishment, operation, and maintenance of effective emergency communications and warning systems. FEMA serves as the White House’s Executive Agent for nationwide systems including the National-level Emergency Alert System (EAS), and as Program Manager for the Department of Homeland Security’s (DHS) Integrated Public Alert and Warning System (IPAWS) among other Contingency Programs and systems. In this role, FEMA is charged with managing large, complex systems involving multiple layers of coordination at the local, state, and federal levels to improve the nation’s communications and warning capabilities. IPAWS and other Contingency Programs are designed to provide Americans with critical and timely hazard alerts and warning information that saves lives and property during emergencies and natural disasters.

To implement the policy established by Executive Order (EO) 13407: Public Alert and Warning System, FEMA directed that an IPAWS Program Management Office (PMO) be established under the management and control of the National Continuity Programs Office (ONCP).  The IPAWS PMO charter provides management and continuity in the development, implementation, operations, and maintenance of the IPAWS programs.

Additionally, subsequent to the issuance of Executive Order 13407, Public Alerts and

Warning System and the recent issuance of the National Communications System (NCS) Directive 3-10, requires close coordination by FEMA ONCP with the newly created National Continuity Coordinator, other elements of DHS and the Federal Executive Branch as a whole in order to achieve mutually supportive and synergistic efforts.

## 1.2	Scope

The IPAWS ISS contract will provide the National Continuity Programs Office (ONCP) with evaluation, development, critical engineering, construction and operational support services related to the ongoing development, testing, certification and sustainment of the IPAWS Program. Specific tasks include but are not limited to the following activities.

### 1.2.1 Inventory, Database and System Evaluation

The ISS contractor may be tasked to document, inventory and evaluate existing Federal, State and Local Government Alert and Warning Systems.  Collected data and reports are intended to describe the inventory of resources (alert and warning equipment in use, components, policies, plans, procedures, staff, facilities) that make up the public alert and warning systems currently used at the Federal, State and local levels of government.  Additional analysis may be required to provide a view of current capabilities of existing public alert and warning systems resources as compared to planned IPAWS capabilities.

### 1.2.2 EAS Modernization and Expansion

The Emergency Alert System (EAS) Commercial Broadcast System is used for broadcasting alerts to the public via commercial radio and television signals.  IPAWS PMO is expanding and modernizing the EAS Commercial Broadcast System.  The largest component of the EAS Commercial Broadcast System consists of Primary Entry Points (PEP).  PEPs are commercial radio stations that the Federal Communication Commission (FCC) has designated as having additional alert and warning responsibilities. The ISS contractor may be tasked to provide PEP station improvements. Projected tasks include design and construction of shelters, fuel storage facilities and site improvements to offer better protection to personnel and infrastructure during emergency conditions.  Additional related efforts may include upgrading existing hardware and software at network facilities and integrating a commercial satellite network into the system.  The contractor may also be required to develop and provide system training.

### 1.2.3 National and State Digital EAS

The Emergency Alert System (EAS) Commercial Broadcast System is predominantly a national level, analog based system that can alert the general pubic through text messaging across television media. IPAWS PMO is enhancing this system to allow digital transmission of audio, text and video messaging across multiple media with the ability to originate alert and warning messages at the state or local level in addition to origination at the national level.  The ISS contractor may be tasked to provide engineering design, system development and system implementation and training of hardware and software enhancements to the EAS to migrate to a digital system as well as operational support and maintenance of delivered equipment. The contractor may be required to support either or both national or state level DEAS implementation efforts.

### 1.2.4 IPAWS Emergency Truck Implementation

The IPAWS PMO has designed and fabricated a mobile communications vehicle for deployment during emergency conditions such as the aftermath of a severe storm to provide interim critical communication to government users across cellular and satellite frequencies pending restoration of fixed services.  The vehicle is utilized for support to both the National Weather Service and Emergency Alert System. The ISS contractor may be tasked to provide integration services of core IPAWS networks to the IPAWS Emergency Truck and provide other operational support services.

### 1.2.5 Additional IPAWS Implementation Services

The ISS contractor may be tasked to provide additional IPAWS implementation services as new requirements for future IPAWS components are defined. These implementation services will be directly associated with IAWS projects that require design and implementation of hardware and software, facility construction or modification, integration, test and delivery of IPAWS components. Implementation services may include collecting and analyzing requirements, developing project implementation plans, performing site preparation and construction, installing hardware and software, conducting system testing, preparing operational and maintenance plans and preparing and delivering associated documentation.

# REFERENCES

The contractor shall ensure that products delivered and work performed under this Statement of Work complies with the following regulations, directives, and standards

## 2.1	General Standards

- Executive Order 13407, Public Alerts and Warning System

- DHS Management Directives (MD 1400, MD 0470.1, MD 11042.1, MD 11050.2)

## 2.2	FEMA Specific Standards

- FEMA Federal Preparedness Circular 65, Federal Executive Branch Continuity of Operations (COOP), dated June 14, 2004

- IPAWS Configuration Management Plan

## 2.3	Technical Standards

- FCC Title 47 Code of Federal Regulations, Chapter 1, Part 11 (“Emergency Alert System”) and Amendments.

- Federal Enterprise Architecture Consolidated Reference Model Document, May 2005

- OASIS Draft Standard 2005.05.15, Common Alerting Protocol v.1.1

- OASIS, Emergency Digital Exchange Language (EDXL) Distribution Element Committee Specification, 14 March 2006

- National Institute of Standards and Technology (NIST) Special Publications, (800-16, 800-26, 800-34, 800-37, 800-50, 800-53) and Federal Information Processing Standards (FIPS) (e.g., FIPS 199).

## 2.4	Security Standards

In general all IPAWS deliverables shall be complaint with DHS and FEMA security policies, requirements, and guidance

- DHS MD 4300A Sensitive Systems Handbook, Version 5.5, September 30, 2007

- Federal Information Security Management Act of 2002 (FISMA)

- DoD 8500-1 Global Information Grid Overarching Policy

- DoD 8500-2 Information Assurance Implementation

- Presidential Decision Memorandum (PDD-63), Critical Infrastructure Protection; May 22, 1998.

## 2.5	Training and Exercises Standards

- Homeland Security Exercise and Evaluation Program (HSEEP) Terminology, Methodology, and Compliance Guidelines Volumes I – III.

# TASKS AND REQUIREMENTS

The contractor shall be responsible for the accuracy, timeliness, and completion of all task orders awarded under this ISS contract and shall furnish all required personnel, materials, facilities, equipment, and support.

## 3.1	Project Management

The contractor shall provide the planning, design, coordination and control necessary to satisfy all requirements contained in this contract.  The Contractor shall determine and establish the project organization to provide overall management of its contract work. The contractor shall designate points of contact responsible for the cost, schedule and technical performance of each awarded task order. These contractor staff shall serve as primary points of contact and they and other staff shall participate in program management review meetings and produce documentation as defined in each task order.

### 3.1.1	Program Planning

The contractor shall coordinate with the IPAWS PMO to develop an Integrated Project Plan that documents how each Task Order under this IDIQ contract contributes to the IPAWS program mission.  The integrated plan shall show the interdependencies of task orders, milestones, and impacts to the overall program effort.

The contractor shall coordinate with the IPAWS PMO on procedures to develop, update, and analyze the Integrated Program Plan.

### 3.1.2	Performance Metrics

The IPAWS PMO will determine the set of metrics to be used on task orders under this contract. Metrics will likely include the following items but may also include task order specific performance requirements:

- Technical accuracy and quality of deliverables which include capability (standards), interoperability and connectivity in addition to data submissions

- Adherence to the delivery schedule

- Responsiveness

The method for Government surveillance will be defined in Task Order Quality Assurance Surveillance Plans (QASP) to be provided with each Task Order.

### 3.1.3	Earned Value Management

The contractor shall tailor an Earned Value Management (EVM) process based on EVM guidelines from the American National Standards Institute/Electronic Industries Alliance (ANSI/EIA) Standard 748-2002, Earned Value Management Systems, May 19, 1998 (revised 2002) and its own practices.  The contractor shall provide EVM status using tailored EVM Report Formats and shall update the report on a monthly basis to show the progress and health of their efforts on Task Orders that specify this reporting requirement.

### 3.1.4	Risk Response Management

As specified in Task Orders, the contractor shall follow the IPAWS PMO risk management strategy for identifying and qualifying risks.  The contractor shall develop and execute a risk process consistent with the IPAWS Risk Management Plan.  With the concurrence of the IPAWS PMO, the contractor shall develop and implement specific strategies for addressing each identified risk, based on the severity of the risk.  For tracking, the contractor shall develop and update regularly a list of risks that reflects their current condition. The contractor shall regularly provide the IPAWS PMO with an updated risk mitigation plan reflecting emerging information and issues and track the effectiveness of strategies designed to mitigate identified risks.

## 3.2 Inventory and Evaluation

The contractor shall perform inventory and evaluation services of existing Federal, State and local government alert and warning systems.

3.2.1 Inventory Reports and Database

The contractor shall inventory and prepare a database of existing alert and warning systems.  Data collected shall include an inventory of resources (alert and warning equipment in use, components, policies, plans, procedures, staff and facilities) The contractor shall utilize an existing or create a new inventory tool, conduct interviews, meetings, inspections, and reviews of all available current alert and warning systems administered or regulated by the United States Government and the States in order to provide a report to assess future public alert and warning system improvements.  This information will be entered into a database for future use.

3.2.2 Inventory Assessment Reports

The contractor shall prepare assessment reports of inventoried systems to document the integrated assessment of the capabilities of the public alert and warning systems to withstand a full range of scenarios from natural disasters to terrorist threats and document post event system capabilities.

3.2.3 System Architecture Reports

The contractor shall provide system architecture reports that provide an assessment of the integration of Federal, State, Territorial, Tribal and local public alert and warning systems.  The contractor shall prepare a report that documents the (as-is) IPAWS Architecture that identifies existing capabilities, leverages best practices and assets used by all levels of government and the private sector and provides a gap analysis that addresses any system and capability shortfalls. The report shall address goals and approaches to rationalize and consolidate systems to address any redundancies and introduce recommended enhancements to the future IPAWS architecture.

## 3.3  Implementation Engineering

The contractor shall perform technical and engineering services associated with IAWS projects requiring design and implementation of hardware and software, facility construction or modification, integration, test and delivery. Implementation engineering services may include preparing plans, collecting and analyzing requirements, documenting system specifications, developing preliminary and final logical and physical system designs, preparing operational and maintenance plans, developing project and implementation plans, and writing all associated documentation.

## 3.4 Facility Design and Construction

The contractor shall accomplish design and construction of necessary structures, or improvements to existing structures, needed to upgrade or modify facilities used for IPAWS systems.  A potential project will support the EAS Commercial Broadcast System PEP stations in enhancing their survivability and operation during times of extreme weather or other natural disasters.  The contractor may be responsible for construction of support structures such as generator aprons or survival shelters.

### 3.4.1 Comprehensive Implementation Plans (CIP)

The contractor shall, at a minimum, define activities, specific approaches, and schedules required in the following paragraphs for each project authorized by Task Order through the preparation of a CIP.

- Estimate time and cost of each project

- Survey, engineer, and accomplish pre-installation activities related to the installation and furnishing of specified items

- Determine interoperability requirements with existing equipment

- Coordinate planning and execution of project work with station managers

- Perform site preparation

- Obtain approvals and permits

- Procurement of supplies and material

- Implementation

- Verification of deliverables

- Restoration of incidental damages to station property

- Verification of completeness.

### 3.4.2 Site Notifications

The contractor shall notify PEP radio station owners or other facility owners before project kickoffs and no later than 5 days before any site work commences.  This notification shall be performed in writing in conjunction with a verbal introduction designed to facilitate cooperation and to answer any questions that the station or other owner might have. Included in this notification will be the Point of Contact (POCs) for the contractor and any associate construction sub contractors.  The notification shall invite the station or other owner and include the date and time of the project kickoff meeting.

### 3.4.3 Work Requirements

The following section describes work requirements relating to facility construction and related activities.

3.4.3.1 Approvals and Permits

The contractor shall obtain all local and regional permits and permissions to perform facility modification and construction as tasked under this contract.  At all sites the building owner's representative shall approve any required construction or changes to the facility.

3.4.3.2 Environmental Compliance

In addition to all other standards and regulations, work that the contractor provides shall comply with national, state, and local environmental requirements.

Environmental impact assessments shall be performed as required and permits obtained before any work permits are issued or work begins.

Any unintended environmental damage or impact caused by work performed on this contract will be reported to appropriate government agencies and to the IPAWS PMO.  In addition, the impacted environment will be restored to a condition acceptable to the site owner and appropriate government agency.  Documentation of satisfactory restoration work will be obtained by the appropriate government agency and provided to the site owner, with copies provided to IPAWS PMO.

After construction has been completed, all work will be verified by the appropriate government agencies for compliance with environment regulations and codes.  Corrective work performed to bring completed work into compliance and acceptance shall be performed and not be charged to IPAWS PMO.

3.4.3.3 Conformity

All work performed by the contractor under this SOW shall conform to all applicable and appropriate national, state, and local construction codes, to all other directives referenced within this contract, and to best practices of commercial industry standard installation and repair procedures.  General installations shall be accomplished in accordance with standard industry practices, standards, and guidelines. The contractor shall maintain on site at all times one copy of the redlined as-built drawings.

3.4.3.4 Documentation and Coordination

Plans (including drawings) shall be complete and shall conform to industry standards before work permits and before digging permits and the like are issued; installation can then start.  In nongovernment facilities, the contractor shall coordinate installation work with the building owner.

## 3.5 Testing and Acceptance

The CIP shall include detailed test plans and procedures for supporting hardware and software installation acceptance. The Contractor shall conduct tests in accordance with the approved CIP.

The Government reserves its right to witness any testing.  The Contractor shall provide a minimum of ten working days notice prior to the conduct of any acceptance testing.  The contractor shall perform necessary adjustments or corrections to any service deficiencies prior to Government acceptance.  Government personnel and/or representative access to the Contractor’s facilities shall be arranged by the Contractor to support this activity. .  The Contractor may also be tasked to support JITC or other associate contractor or Government Agency testing of IPAWS components.

## 3.6 System Configuration

Following delivery and acceptance of IPAWS equipment or systems, the contractor may be tasked to maintain configuration management of the system, for hardware, software, and coding so that system standards are maintained throughout all deployments.  Configuration data shall include the appropriate warranty information for all delivered products

## 3.7 Operations and Maintenance Support.

As directed by Task Order, the contractor shall provide operations and maintenance support services for delivered IPAWS systems or components. Services shall include but are not limited to the following items:

•	System monitoring

•	Preventative maintenance for routine connectivity and equipment care

•	Equipment replacement/sparing/repair

•	Incident reporting

•	Problem troubleshooting, diagnosis, fixes and resolution

•	Application patches and release implementation for corrective measures and system improvements and new functionality

•	Personnel staffing and skill required for system operations and maintenance

•	Logistics for housing the personnel, equipment and spares necessary for O&M

•	Physical security reviews and vulnerabilities assessment

# 4	PERSONNEL SECURITY

The contractor is required to hold valid security clearances, to include TOP SECRET/SCI, to complete portions of the tasks identified in this performance work statement, such as installing equipment into FEMA facilities. Most of the work to be completed by the contractor will be unclassified.  However, all documents generated that are related to this project shall include, as a minimum, the protective footer marking, “Not for Public Release,” unless otherwise directed by the government COTR.

All key personnel shall have active TS clearances and be eligible for SCI. All non-key personnel shall be able to meet clearances requirements as determined by the requirements of the tasks.

All data, software, equipment, analysis results, and reports and briefings generated during this contract are the property of the U.S. government and not releasable to third parties without express written consent of COTR

The contractor is responsible for providing all information to FEMA Security personnel for screening of the employees as required.  All key personnel shall have TOP Secret clearances at time of award.  A DD-254 “Contract Security Classification” is required for this contract and some individual task order.

# 5	NONDISCLOSURE OF SENSITIVE AND/OR PROPRIETARY DATA

The contractor recognizes that in the performance of this contract it may receive or have access to certain sensitive information, including information provided on a proprietary basis by other contractors, equipment manufacturers and other private or public entities.  The contractor agrees to use and examine this information exclusively in the performance of this contract and to take the necessary steps in accordance with Government regulations to prevent disclosure of such information to any party outside the Government or Government-designated support contractors possessing appropriate proprietary agreements, as listed in paragraphs a. through d. below.

a. Indoctrination of Personnel.

The contractor agrees to indoctrinate its personnel who have access as to the sensitive nature of the information and the relationship under which the contractor has possession of or access to the information.  Contractor personnel shall not engage in any other action, venture or employment wherein sensitive information will be used for the profit of any party other than those furnishing the information.  The Nondisclosure Agreement for Contractor Employees at Appendix B shall be signed by all indoctrinated personnel and forwarded to the COTR for retention, prior to commencement of work.  The contractor shall restrict access to sensitive/ proprietary information to the minimum number of employees necessary for contract performance.

b. Signed Agreements.

(1)  The contractor further agrees to sign an agreement to this effect with any private or public entities providing proprietary data for performance under this contract.  As part of this agreement, the contractor shall inform all parties of its agreement to allow certain Government-designated contractors access to all data as described in paragraph c., below.  One copy of each signed agreement shall be forwarded to the Contracting Officer (CO).  These shall be signed prior to work commencing.

(2)  In addition, the contractor shall be required to coordinate and exchange directly with other contractors as designated by the Government for information pertinent and essential to performance of work under this contract.  The contractor shall discuss and attempt to resolve any problems between the contractor and those contractors designated by the Government.  The CO shall be notified in writing of any disagreement (s) which has (have) not been resolved in a timely manner.  Furnish the CO copies of communications between the contractor and associate contractor(s) relative to contract performance.  Further, the close interchange with between contractor(s) may require access to or release of proprietary data.  In such an event, the contractor shall enter into agreement(s) with the Government designated contractor (s) to adequately protect such proprietary data from unauthorized use or disclosure so long as it remains proprietary.  A copy of such agreement shall be provided to the CO.

c. Government-Designated Contractors.

The contractor agrees to allow the below listed Government-designated support contractors, possessing appropriate nondisclosure agreements and retained by the Government to advise the Government on cost, schedule and technical matters pertaining to this acquisition, access to any limited rights data acquired under the terms and conditions of this contract.  List designated contractors:

Booz Allen Hamilton

Five Rivers LLC

All Government-designated contractors stated herein, or added at a future date shall also enter into nondisclosure agreements with all parties providing proprietary information to the contractor, and the nondisclosure agreements shall be signed before work commences.

d. Remedy for Breach.

The contractor agrees that any breach or violation of the certifications or restrictions of this clause shall constitute a material and substantial breach of the terms, conditions and provisions of the contract and that the Government may, in addition to any other remedy available, terminate this contract for default.